## approved_records
document_id | document_type | source_file | asset_id | asset_name | site | request_date | event_date | priority | status | issue_category | failure_description | recommended_action | requester | technician | vendor_name | part_code | part_name | quantity | estimated_cost | downtime_hours | normalized_issue_category | severity_score | urgency_flag | missing_information_flag | summary_for_business | route_to_team | extraction_confidence | raw_text_excerpt
WO-1001 | maintenance_work_order | WO-1001.txt | PMP-210 | Booster Pump A | RIO | 2026-07-02 | 2026-07-02 | critical | open | mechanical | Abnormal vibration near coupling and oil leak around seal housing. | Inspect alignment, replace seal, and validate bearing condition. | Mariana Costa | [5 empty] | 7800 | 6.5 | mechanical | 100 | high | no | maintenance_work_order for PMP-210 at RIO with critical priority. Abnormal vibration near coupling and oil leak around seal housing. | mechanical_team | 0.92 | Work Order: WO-1001 Asset ID: PMP-210 Asset Name: Booster Pump A Site: RIO Request Date: 2026-07-02 Priority: critical Category: mechanical Requester: Mariana Costa Failure Descrip
WO-1002 | maintenance_work_order | WO-1002.txt | CMP-115 | Air Compressor 2 | MCZ | 2026-07-03 | 2026-07-03 | high | in_progress | electrical | Motor trip observed twice during peak load. | Check MCC panel, cable insulation, and overload settings. | Felipe Ramos | [5 empty] | 4300 | 3.0 | electrical | 75 | high | no | maintenance_work_order for CMP-115 at MCZ with high priority. Motor trip observed twice during peak load. | electrical_team | 0.92 | Work Order: WO-1002 Asset ID: CMP-115 Asset Name: Air Compressor 2 Site: MCZ Request Date: 2026-07-03 Priority: high Category: electrical Requester: Felipe Ramos Failure Descriptio
WO-1003 | maintenance_work_order | WO-1003.txt | VLV-332 | Control Valve 7 | SSA | 2026-07-04 | 2026-07-04 | medium | open | instrumentation | Position feedback inconsistent with local indicator. | Recalibrate positioner and inspect signal wiring. | Ana Beatriz | [5 empty] | 1600 | 1.5 | instrumentation | 55 | normal | no | maintenance_work_order for VLV-332 at SSA with medium priority. Position feedback inconsistent with local indicator. | instrumentation_team | 0.92 | Work Order: WO-1003 Asset ID: VLV-332 Asset Name: Control Valve 7 Site: SSA Request Date: 2026-07-04 Priority: medium Category: instrumentation Requester: Ana Beatriz Failure Descr
WO-1004 | maintenance_work_order | WO-1004.txt | Asset Name: Cooling Fan 4 | Cooling Fan 4 | VIX | 2026-07-05 | 2026-07-05 | high | open | mechanical | Excessive noise reported during startup. | Inspect blades and fastening points. | Carlos Nunes | [5 empty] | 1200 | 2.0 | mechanical | 75 | high | no | maintenance_work_order for Asset Name: Cooling Fan 4 at VIX with high priority. Excessive noise reported during startup. | mechanical_team | 0.92 | Work Order: WO-1004 Asset ID: Asset Name: Cooling Fan 4 Site: VIX Request Date: 2026-07-05 Priority: high Category: mechanical Requester: Carlos Nunes Failure Description: Excessiv
WO-1006 | maintenance_work_order | WO-1006.txt | PMP-455 | Transfer Pump B | RIO | 2026-07-07 | 2026-07-07 | low | closed | inspection | Routine inspection created for small casing paint damage. | Schedule coating touch-up in next maintenance window. | Luciana Alves | [5 empty] | 350 | 0.0 | inspection | 35 | normal | no | maintenance_work_order for PMP-455 at RIO with low priority. Routine inspection created for small casing paint damage. | inspection_team | 0.92 | Work Order: WO-1006 Asset ID: PMP-455 Asset Name: Transfer Pump B Site: RIO Request Date: 2026-07-07 Priority: low Category: inspection Requester: Luciana Alves Failure Description
WO-1008 | maintenance_work_order | WO-1008.txt | TK-120 | Storage Tank 12 | SSA | 2026-07-09 | 2026-07-09 | medium | approved | inspection | Level gauge verification requested before audit. | Perform inspection and record calibration evidence. | Julio Moreira | [5 empty] | 800 | 1.0 | inspection | 55 | normal | no | maintenance_work_order for TK-120 at SSA with medium priority. Level gauge verification requested before audit. | inspection_team | 0.92 | Work Order: WO-1008 Asset ID: TK-120 Asset Name: Storage Tank 12 Site: SSA Request Date: 2026-07-09 Priority: medium Category: inspection Requester: Julio Moreira Failure Descripti
IN-3001 | inspection_checklist | inspection_batch_a.csv | PMP-210 |  | RIO |  | 2026-07-02 | high | open | inspection | Thermography found hot coupling area. | Schedule vibration route and thermal follow-up. | [8 empty] | inspection | 75 | high | no | inspection_checklist for PMP-210 at RIO with high priority. Thermography found hot coupling area. | inspection_team | 0.92 | document_id=IN-3001 event_date=2026-07-02 asset_id=PMP-210 site=RIO priority=high issue_category=inspection failure_description=Thermography found hot coupling area. recommended_ac
IN-3002 | inspection_checklist | inspection_batch_a.csv | TK-120 |  | SSA |  | 2026-07-03 | low | closed | inspection | No abnormality detected. Routine compliance check. | Close checklist and archive evidence. | [8 empty] | inspection | 35 | normal | no | inspection_checklist for TK-120 at SSA with low priority. No abnormality detected. Routine compliance check. | inspection_team | 0.92 | document_id=IN-3002 event_date=2026-07-03 asset_id=TK-120 site=SSA priority=low issue_category=inspection failure_description=No abnormality detected. Routine compliance check. rec
IN-3003 | inspection_checklist | inspection_batch_a.csv | CMP-115 |  | MCZ |  | 2026-07-04 | medium | open | inspection | Air line moisture above expected range. | Inspect dryer and drain schedule. | [8 empty] | inspection | 55 | normal | no | inspection_checklist for CMP-115 at MCZ with medium priority. Air line moisture above expected range. | inspection_team | 0.92 | document_id=IN-3003 event_date=2026-07-04 asset_id=CMP-115 site=MCZ priority=medium issue_category=inspection failure_description=Air line moisture above expected range. recommende
IN-3004 | inspection_checklist | inspection_batch_a.csv | VLV-332 |  | SSA |  | 2026-07-05 | medium | open | instrumentation | Signal fluctuation during travel test. | Inspect cabling and calibration setup. | [8 empty] | instrumentation | 55 | normal | no | inspection_checklist for VLV-332 at SSA with medium priority. Signal fluctuation during travel test. | instrumentation_team | 0.92 | document_id=IN-3004 event_date=2026-07-05 asset_id=VLV-332 site=SSA priority=medium issue_category=instrumentation failure_description=Signal fluctuation during travel test. recomm
IN-3006 | inspection_checklist | inspection_batch_a.csv | GEN-808 |  | MCZ |  | 2026-07-07 | high | open | electrical | Starter test failed due to voltage drop. | Prioritize battery replacement. | [8 empty] | electrical | 75 | high | no | inspection_checklist for GEN-808 at MCZ with high priority. Starter test failed due to voltage drop. | electrical_team | 0.92 | document_id=IN-3006 event_date=2026-07-07 asset_id=GEN-808 site=MCZ priority=high issue_category=electrical failure_description=Starter test failed due to voltage drop. recommended
VR-4001 | vendor_service_request | VR-4001.txt | HTX-901 |  | RIO | 2026-07-05 | 2026-07-08 | high | pending_vendor | vendor_support | Requesting cleaning contractor mobilization for exchanger fouling. | Confirm availability and quote window. |  |  | ThermoServ |  |  |  | 12500 |  | vendor_support | 80 | high | no | vendor_service_request for HTX-901 at RIO with high priority. Requesting cleaning contractor mobilization for exchanger fouling. | vendor_management | 0.92 | Subject: Service Request VR-4001 for HTX-901 Request Date: 2026-07-05 Required By: 2026-07-08 Site: RIO Priority: high Vendor: ThermoServ Category: vendor_support Details: Requesti
VR-4002 | vendor_service_request | VR-4002.txt | GEN-808 |  | MCZ | 2026-07-06 | 2026-07-10 | critical | open | vendor_support | Need urgent delivery of startup battery modules. | Expedite vendor response and reserve test team. |  |  | PowerCore |  |  |  | 9400 |  | vendor_support | 95 | high | no | vendor_service_request for GEN-808 at MCZ with critical priority. Need urgent delivery of startup battery modules. | vendor_management | 0.92 | Subject: Service Request VR-4002 for GEN-808 Request Date: 2026-07-06 Required By: 2026-07-10 Site: MCZ Priority: critical Vendor: PowerCore Category: vendor_support Details: Need
VR-4004 | vendor_service_request | VR-4004.txt | CMP-115 |  | MCZ | 2026-07-08 | 2026-07-12 | high | in_progress | electrical | Specialist support requested for MCC inspection. | Coordinate shutdown slot and access permit. |  |  | ElectroWorks |  |  |  | 6200 |  | electrical | 75 | high | no | vendor_service_request for CMP-115 at MCZ with high priority. Specialist support requested for MCC inspection. | electrical_team | 0.92 | Subject: Service Request VR-4004 for CMP-115 Request Date: 2026-07-08 Required By: 2026-07-12 Site: MCZ Priority: high Vendor: ElectroWorks Category: electrical Details: Specialist
PR-5001 | spare_parts_request | parts_requests_july.csv | PMP-210 |  | RIO | 2026-07-05 | 2026-07-05 | high | approved | general_ops |  |  | Mariana Costa |  |  | SEAL-44 | Mechanical Seal Kit | 1 | 1200 |  | general_ops | 75 | high | no | spare_parts_request for PMP-210 at RIO with high priority. No failure description provided. | operations_support | 0.92 | document_id=PR-5001 request_date=2026-07-05 asset_id=PMP-210 site=RIO priority=high requester=Mariana Costa part_code=SEAL-44 part_name=Mechanical Seal Kit quantity=1 estimated_cos
PR-5002 | spare_parts_request | parts_requests_july.csv | CMP-115 |  | MCZ | 2026-07-06 | 2026-07-06 | high | approved | general_ops |  |  | Felipe Ramos |  |  | RELAY-19 | Overload Relay | 2 | 900 |  | general_ops | 75 | high | no | spare_parts_request for CMP-115 at MCZ with high priority. No failure description provided. | operations_support | 0.92 | document_id=PR-5002 request_date=2026-07-06 asset_id=CMP-115 site=MCZ priority=high requester=Felipe Ramos part_code=RELAY-19 part_name=Overload Relay quantity=2 estimated_cost=900
PR-5003 | spare_parts_request | parts_requests_july.csv | GEN-808 |  | MCZ | 2026-07-07 | 2026-07-07 | critical | open | general_ops |  |  | Daniel Rocha |  |  | BAT-88 | Industrial Battery Module | 4 | 4800 |  | general_ops | 95 | high | no | spare_parts_request for GEN-808 at MCZ with critical priority. No failure description provided. | operations_support | 0.92 | document_id=PR-5003 request_date=2026-07-07 asset_id=GEN-808 site=MCZ priority=critical requester=Daniel Rocha part_code=BAT-88 part_name=Industrial Battery Module quantity=4 estim
PR-5004 | spare_parts_request | parts_requests_july.csv | VLV-332 |  | SSA | 2026-07-08 | 2026-07-08 | medium | closed | general_ops |  |  | Ana Beatriz |  |  | AIR-22 | Pneumatic Filter | 1 | 220 |  | general_ops | 55 | normal | no | spare_parts_request for VLV-332 at SSA with medium priority. No failure description provided. | operations_support | 0.92 | document_id=PR-5004 request_date=2026-07-08 asset_id=VLV-332 site=SSA priority=medium requester=Ana Beatriz part_code=AIR-22 part_name=Pneumatic Filter quantity=1 estimated_cost=22